## Sheet1
Displaying 166 issues at 2018-05-17 20:12.
Key | Summary | Issue Type | Updated | Status | Severity | Component/s | Issue reproduced | Comments
TEL_L2300_A01_GM-1375 | Notification Bar/ Status Bar | Bug | 2017-12-12 14:44 | NotBug | A-Critical | Dailybuild, Display |  | Not an issue as per GM comments
TEL_L2300_A01_GM-1380 | Performance (Video Play) Issue | Bug | 2017-12-07 19:59 | NotBug | S-Blocking | Video | No
TEL_L2300_A01_GM-1410 | [Application] 3rd Party App Crash - "YDS-YOKDIL Test Uzmanı" [User:Zeynep] | Bug | 2018-02-21 16:00 | NotBug | C-Minor | 3rd app |  | Not tested (Need more info about 3rd party app)
TEL_L2300_A01_GM-1412 | wifi shutdown problem [User:Zeynep] | Bug | 2018-02-21 17:48 | NotBug | A-Critical | WiFi |  | Not an issue as per GM comments
TEL_L2300_A01_GM-1421 | Dolby Atmos_name | Bug | 2017-12-22 20:53 | NotBug | A-Critical | 3rd app, Display, Status bar |  | This is feature enhancement in latest build O1GM18C
TEL_L2300_A01_GM-1426 | Whatsapp Name don't appear | Bug | 2017-12-11 21:03 | NotBug | A-Critical | 3rd app |  | Not an issue as per GM comments
TEL_L2300_A01_GM-1430 | [Turkcell] [Vodafone] Wifi Preference Setting | Bug | 2018-01-15 14:18 | Suspended | B-Major | Network |  | Not tested -Turkcell, vodafone
TEL_L2300_A01_GM-1431 | [Turkcell] [Vodafone] [Turk Telekom] Video Call Hold | Bug | 2017-12-29 15:46 | NotBug | A-Critical | Call, Network |  | Not tested - Turkcell, vodafone
TEL_L2300_A01_GM-1438 | [Function] Lock Screen Notification | Bug | 2018-01-02 19:07 | NotBug | B-Major | Lock screen |  | Not an issue as per GM comments
TEL_L2300_A01_GM-1440 | [Application] Phone App (Dialar) | Bug | 2017-12-27 15:58 | NotBug | A-Critical | 3rd app | No
TEL_L2300_A01_GM-1460 | [TurkTelekom] Volte --> 2G Silent Call | Bug | 2018-03-26 17:46 | Suspended | S-Blocking | Call |  | Not tested (Turk telekom)
TEL_L2300_A01_GM-1472 | [Function] Adaptive Brightness Problem | Bug | 2018-01-02 20:52 | NotBug | B-Major | Display, LCD, Sensor | No
TEL_L2300_A01_GM-1475 | [Translation] Select to Speak => Seç ve Dinle | Bug | 2018-01-02 11:42 | NotBug | B-Major | Settings | No
TEL_L2300_A01_GM-1476 | [Turkcell] [Vodafone] Wifi Calling - Mobile Preferred | Bug | 2018-01-15 14:19 | Suspended | A-Critical | Call, Network, WiFi |  | Not tested -Turk cell, vodafone
TEL_L2300_A01_GM-1479 | [Application] Video Call Video Sprawl Issue | Bug | 2017-12-28 19:12 | NotBug | B-Major | Call, Camera, Video | No
TEL_L2300_A01_GM-1481 | [Turkcell] Video Calling Problem | Bug | 2018-01-10 21:07 | NotBug | B-Major | Call |  | Not tested (Turk cell)
TEL_L2300_A01_GM-1483 | [Application] Facebook Live Video Feature | Bug | 2018-01-30 16:19 | NotBug | C-Minor | 3rd app | No
TEL_L2300_A01_GM-1486 | [Application] Facebook- error at first installation | Bug | 2018-02-01 17:14 | NotBug | A-Critical | 3rd app(operator) | No
TEL_L2300_A01_GM-1492 | [Roaming] Operator Names- Double Sim Card | Bug | 2017-12-28 23:16 | NotBug | C-Minor | 3rd app(operator) |  | Not tested due to lack of turkey operator(SIMs)
TEL_L2300_A01_GM-1493 | [Application] Phone Dialar Crash on Dual Device | Bug | 2017-12-28 19:16 | NotBug | A-Critical | 3rd app, Call | No
TEL_L2300_A01_GM-1494 | [Application] WhatsApp - Contacts Acount Problem [User:Zeynep] | Bug | 2018-02-21 17:47 | NotBug | B-Major | Contacts |  | Need more info on why it is not a bug
TEL_L2300_A01_GM-1495 | [Internal Call] Video Call Icon | Bug | 2017-12-28 17:27 | NotBug | C-Minor | Call, Video |  | Not tested due to lack of turkey operator(SIMs)
TEL_L2300_A01_GM-1499 | [Application] Dolby and Files | Bug | 2018-01-08 16:58 | NotBug | B-Major | 3rd app | No
TEL_L2300_A01_GM-1503 | [Function] Application doesn't Fill the Fullscreen | Bug | 2018-02-01 15:42 | NotBug | C-Minor | Display | No
TEL_L2300_A01_GM-1504 | [Function] Handover - Call Screen 4G - Turk Telekom | Bug | 2018-01-23 09:10 | Suspended | B-Major | 3rd app(operator), Call |  | Not tested (Turk telekom)
TEL_L2300_A01_GM-1508 | [Function] Drop to 3G at Video Call - Turk Telekom | Bug | 2018-01-15 14:18 | Suspended | B-Major | Call, Video |  | Not tested (Turk telekom)
TEL_L2300_A01_GM-1510 | [Turk Telekom] Call ends from 4G to 3G at Handover | Bug | 2018-01-15 14:19 | Suspended | B-Major | Call |  | Not tested (Turk telekom)
TEL_L2300_A01_GM-1511 | [General] Outlook Crash | Bug | 2018-01-11 21:39 | NotBug | B-Major | 3rd app(operator) | No
TEL_L2300_A01_GM-1513 | Screen Lock Settings ( Lock Screen Message ) | Bug | 2018-01-02 15:10 | NotBug | C-Minor | Settings |  | This is feature enhancement in latest build O1GM18C
TEL_L2300_A01_GM-1517 | [Translation] Operator's names instead of CARD 1 and CARD 2 | Bug | 2018-01-04 19:07 | NotBug | C-Minor | Settings, Simcard | No
TEL_L2300_A01_GM-1522 | [General] Home screen feature after on first install | Bug | 2018-01-04 20:39 | NotBug | B-Major | Main Screen |  | This is feature enhancement in latest build O1GM18C
TEL_L2300_A01_GM-1523 | [General] Display Spread | Bug | 2018-01-16 08:54 | Unsured | B-Major | Display |  | Need more info on why it is unsured
TEL_L2300_A01_GM-1526 | [Vodafone] While making emergency calls on VoWiFi attached | Bug | 2018-02-23 11:10 | Suspended | B-Major | Network |  | Not tested (vodafone)
TEL_L2300_A01_GM-1530 | [Application] Files App | Bug | 2018-01-05 21:25 | NotBug | B-Major | 3rd app | No
TEL_L2300_A01_GM-1531 | [Application] Files App | Bug | 2018-01-15 22:24 | NotBug | B-Major | 3rd app | No | Duplicate of GM-1530
TEL_L2300_A01_GM-1538 | [General] Bluetooth Headphone | Bug | 2018-01-16 14:26 | NotBug | B-Major | Bluetooth, Earphone, Lock screen | No
TEL_L2300_A01_GM-1543 | [Function]Camera-Panorama-Problem [User:Hilal] | Bug | 2018-02-21 17:50 | NotBug | B-Major | Camera | No
TEL_L2300_A01_GM-1546 | [Function]AddingWiFi_UsingWEPsecurity_Password_Problem [User:Hilal] | Bug | 2018-02-21 17:49 | NotBug | B-Major | WiFi |  | Not an issue as per GM comments
TEL_L2300_A01_GM-1550 | [Turkcell] While making emergency calls on VoWiFi attached | Bug | 2018-02-23 11:06 | Suspended | A-Critical | Settings |  | Not tested -Turkcell
TEL_L2300_A01_GM-1551 | [General] No Ringtone Sound | Bug | 2018-01-17 21:32 | NotBug | B-Major | Call, Settings | No
TEL_L2300_A01_GM-1552 | [General] Calling Voice Quality [User:Zeynep] | Bug | 2018-02-21 17:47 | NotBug | A-Critical | Call |  | Need more info on why it is not a bug
TEL_L2300_A01_GM-1553 | [TurkTelekom] Video Call - Camera On/Off Button | Bug | 2018-01-19 19:50 | NotBug | B-Major | Call, Video |  | Not tested (Turk telekom)
TEL_L2300_A01_GM-1554 | GM8_OGM18B_vSRVCC_Problem [User:Zeynep/Hilal] | Bug | 2018-02-21 17:16 | Unsured | A-Critical | Call |  | Not tested (SRVCC)
TEL_L2300_A01_GM-1557 | SRVCC_MT Call_Turk_Telekom | Bug | 2018-05-02 17:03 | Unsured | S-Blocking | Call |  | Not tested (SRVCC)
TEL_L2300_A01_GM-1560 | [Function]Camera-VideoTransition-Problem [User:Hilal] | Bug | 2018-02-21 17:46 | NotBug | A-Critical | Camera | No | But during transition from camera to video sound is producing even media volume is low.this issue was raised in JIRA and Longcheer
TEL_L2300_A01_GM-1562 | [Function]Camera-Rear/Front-Missing Modes [User:Hilal] | Bug | 2018-02-21 17:46 | NotBug | A-Critical | Camera |  | This is feature enhancement in latest build O1GM18C
TEL_L2300_A01_GM-1572 | [Function]VoLTEtoVT_UpgradeRequest_on_SleepMode [User:Hilal] | Bug | 2018-02-21 17:43 | NotBug | A-Critical | Call |  | Not tested - IMS registration is not done
TEL_L2300_A01_GM-1573 | [Function] Fingerprint Improvement | Bug | 2018-02-01 15:39 | NotBug | B-Major | Fingerprint | No
TEL_L2300_A01_GM-1575 | [Vodafone] Can't make MT ViLTE Call [User:Hilal/Erol] | Bug | 2018-03-29 19:33 | Suspended | B-Major | Call |  | Not tested -Vodafone
TEL_L2300_A01_GM-1576 | [Function] Help Icon | Bug | 2018-04-28 11:29 | Unsured | B-Major | Settings |  | This is feature enhancement in latest build O1GM18C
TEL_L2300_A01_GM-1578 | Camera_Auto_Mode_Icon [User:Zeynep] | Bug | 2018-05-17 14:40 | NotBug | A-Critical | Camera | No
TEL_L2300_A01_GM-1579 | Camera_Slow_Motion_New_Feature [User:Zeynep] | Bug | 2018-02-21 17:04 | NotBug | A-Critical | Camera | No
TEL_L2300_A01_GM-1581 | [Function]Camera-Video-Flash [User:Hilal] | Bug | 2018-02-21 17:42 | NotBug | A-Critical | Camera | No | This feature was removed in latest build O1GM18C
TEL_L2300_A01_GM-1585 | HDR_Mode_Change [User:Zeynep] | Bug | 2018-02-21 17:17 | NotBug | B-Major | Camera |  | Not an issue(this is feature in latest build)
TEL_L2300_A01_GM-1586 | [General] Device Freeze Spontaneously | Bug | 2018-05-17 15:13 | NotBug | A-Critical | Poweron/off | No
TEL_L2300_A01_GM-1587 | GM8 Network Icon | Bug | 2018-01-24 15:24 | NotBug | A-Critical | Display, Status bar |  | Need more info on why it is not a bug
TEL_L2300_A01_GM-1592 | Bluetooth_Headset_DUT_Crash [User:Hilal] | Bug | 2018-02-21 17:39 | NotBug | A-Critical | Bluetooth | No
TEL_L2300_A01_GM-1596 | [Network] Wi-Fi Hotspot AP Band | Bug | 2018-02-07 15:03 | NotBug | A-Critical | Network, Settings, WiFi |  | As per GM comments, Android design it is expected behaviour
TEL_L2300_A01_GM-1598 | [Function] VT Call and Options | Bug | 2018-01-30 21:45 | NotBug | B-Major | Call, Settings | No
TEL_L2300_A01_GM-1599 | [Function] Video Call Hold | Bug | 2018-03-06 15:23 | NotBug | A-Critical | Call, Video |  | For latest build call hold and resume icons are not present
TEL_L2300_A01_GM-1600 | [Function] Video Call from other phone Hold&Resume | Bug | 2018-03-06 11:24 | Unsured | A-Critical | Call, Video |  | In latest build when DUT is in two VT calls,the audio of first VT call is only audible even though it went to hold but no issue in video
TEL_L2300_A01_GM-1601 | [General] GM Service Crash | Bug | 2018-05-16 16:45 | NotBug | C-Minor | 3rd app, Settings, WiFi |  | Not tested due to public network(railway stations, starbucks..etc)
TEL_L2300_A01_GM-1604 | [General] Translation Error | Bug | 2018-02-01 17:48 | NotBug | A-Critical | Charging, String | No
TEL_L2300_A01_GM-1606 | [General] Cast screen is searching for devices without WiFi enabled and rotate feature | Bug | 2018-05-10 17:10 | Unsured | B-Major | Display, Settings, WiFi | Yes | GAO-44
TEL_L2300_A01_GM-1612 | [General] Edit captured video in Gallery App | Bug | 2018-02-06 20:20 | NotBug | B-Major | 3rd app, Gallery |  | Depends on 3rd party gallery app
TEL_L2300_A01_GM-1613 | [General] While browsing "Android stoped" pops up | Bug | 2018-03-03 15:58 | Suspended | B-Major | 3rd app | No | But while performing these steps, the system crash did not happen but GM Music has crashed.
TEL_L2300_A01_GM-1614 | [General] Incoming Call- Media play | Bug | 2018-05-10 20:47 | NotBug | B-Major | Call, Music, Settings, Video |  | Not an issue due to lack of turkey operator
TEL_L2300_A01_GM-1616 | WiFi Hotspot works in single band (only 2.4Ghz) without sim | Bug | 2018-02-07 15:12 | NotBug | B-Major | WiFi |  | Duplicate of GM_1596
TEL_L2300_A01_GM-1617 | [General] Monkey testing devices is rebooting in every few mins | Bug | 2018-02-15 17:13 | NotBug | A-Critical | Poweron/off |  | Not tested -Monkey Testing
TEL_L2300_A01_GM-1619 | Hangout isn't Responding [User:Hilal] | Bug | 2018-02-21 17:32 | Unsured | A-Critical | 3rd app | Yes | GAO-56
TEL_L2300_A01_GM-1621 | [General] Unable to create a new contact from Dialer App to Device Folder | Bug | 2018-02-15 17:05 | NotBug | B-Major | Call, Call History, Contacts | No
TEL_L2300_A01_GM-1622 | [General]Phone app crash while the FM is in background | Bug | 2018-02-27 18:52 | Suspended | B-Major | 3rd app, Call | No
TEL_L2300_A01_GM-1623 | [General] Bluetooth A2DP Music stops playing | Bug | 2018-03-09 17:24 | Suspended | B-Major | Bluetooth, Music | Yes | GAO-152
TEL_L2300_A01_GM-1625 | [General] USB - When the DUT is connected to system it detects as MTP | Bug | 2018-02-15 21:14 | Unsured | C-Minor | USB & OTG |  | Not an issue as per the general feature
TEL_L2300_A01_GM-1626 | [General] Factory reset boot-up time | Bug | 2018-02-28 11:09 | Unsured | C-Minor | Poweron/off |  | Need more info
TEL_L2300_A01_GM-1629 | DUT getting FATAL ERROR | Bug | 2018-03-01 09:35 | Unsured | B-Major | 3rd app, Settings | No
TEL_L2300_A01_GM-1630 | [General] sleep current ıs consumıng 5.17ma | Bug | 2018-05-11 18:44 | Suspended | S-Blocking | Power Management |  | Not tested - thermal testing
TEL_L2300_A01_GM-1631 | Feature Requirement: EVS Codec | Bug | 2018-05-07 11:15 | Unsured | B-Major | Call |  | Not tested - Vodafone
TEL_L2300_A01_GM-1632 | [Network] Uplink Multi-Cluster Support | Bug | 2018-02-15 21:45 | NotBug | B-Major | Network |  | Need info
TEL_L2300_A01_GM-1633 | [General] HOLD arrow button is not displaying in manage conference call in manage list. | Bug | 2018-03-06 19:14 | Unsured | B-Major | Call, Contacts | No
TEL_L2300_A01_GM-1639 | [General] Camera Switching Sound in Video Call is inappropriate | Bug | 2018-03-02 16:38 | Suspended | B-Major | Call, Video | No
TEL_L2300_A01_GM-1641 | Camera_Mode_Setting_Change [User:Hilal] | Bug | 2018-03-14 17:03 | Suspended | B-Major | Camera | No
TEL_L2300_A01_GM-1643 | Boot-up Screen While DUT has a password | Bug | 2018-03-27 14:55 | NotBug | A-Critical | Poweron/off |  | Its not a bug..Its a google default design
TEL_L2300_A01_GM-1650 | GM8_Camera: GPS location option is disabled when camera launched from lock screen | Bug | 2018-05-16 20:23 | NotBug | B-Major | Camera, GPS | Yes | Need more info why it is NOT A BUG(already raised in JIRA GAO-162)
TEL_L2300_A01_GM-1651 | GMOffice_WiFi Thermal front-end module is heating up to 36C without WiFi/BT ON | Bug | 2018-03-09 09:59 | Unsured | A-Critical | Bluetooth, WiFi |  | Not Tested -Thermal testing (Raised in JIRA GAO-193)
TEL_L2300_A01_GM-1653 | Camera error tone not played saving to SD card when SD card is not present | Bug | 2018-03-03 10:35 | Unsured | B-Major | Camera |  | Its not a bug..Its a google default design
TEL_L2300_A01_GM-1654 | [Network] DUT unable to hangup the call in during OOS (Out of Service) | Bug | 2018-03-14 19:56 | Suspended | B-Major | Call, Network |  | Not Tested -need more info
TEL_L2300_A01_GM-1657 | GM8 : WiFi connection to last connected AP fails randomly after entering wrong password | Bug | 2018-05-17 13:50 | Unsured | B-Major | WiFi | No
TEL_L2300_A01_GM-1661 | [Connectivity] WLAN connection lost while receiving Drone's real time video | Bug | 2018-03-09 17:23 | Suspended | A-Critical | Bluetooth, GPS, WiFi |  | Not tested -related to another project
TEL_L2300_A01_GM-1662 | [Camera]Image stabilization | Bug | 2018-02-28 18:03 | Unsured | B-Major | Camera | yes | GAO-282
TEL_L2300_A01_GM-1665 | [Network] Conference Call UI _ Manage Call is missing | Bug | 2018-03-03 11:09 | Unsured | B-Major | Call, Network | No
TEL_L2300_A01_GM-1666 | Launch latency in Dialed call list while checking dialer app | Bug | 2018-03-28 20:03 | Unsured | B-Major | Call, Call History | No
TEL_L2300_A01_GM-1668 | [General] Bootup_keyboard flicker in PIN lock screen | Bug | 2018-02-27 16:30 | Unsured | B-Major | Poweron/off, Settings | Yes | GAO-165
TEL_L2300_A01_GM-1669 | [General] GMOffice_Bootup_PIN check for Lock Screen is taking 3 seconds time | Bug | 2018-03-09 15:01 | Unsured | B-Major | Power Management, Settings | Yes | GAO-163
TEL_L2300_A01_GM-1670 | [General] Bootup is taking longer than expected with PIN lock enabled | Bug | 2018-02-28 16:53 | Unsured | B-Major | Poweron/off, Settings |  | NOT A BUG as per the GM comments
TEL_L2300_A01_GM-1672 | Performance: Device fails to keep more than 3 activities | Bug | 2018-03-14 14:47 | Unsured | A-Critical | Runintest, Settings | Yes | GAO-76
TEL_L2300_A01_GM-1673 | Thermal Temperature is reaching till 44C while Video recording with flash & GPS | Bug | 2018-03-09 10:12 | Unsured | A-Critical | Camera, Power Management, Video |  | Not tested - thermal testing(raised in JIRA GAO-179)
TEL_L2300_A01_GM-1674 | Camera crashed at some point of thermal stress | Bug | 2018-05-16 15:57 | Suspended | A-Critical | Camera, Power Management |  | Not tested - thermal testing(raised in JIRA GAO-172)
TEL_L2300_A01_GM-1677 | Observed null object reference error while choosing internal storage of SD card | Bug | 2018-04-27 17:49 | NotBug | B-Major | System Tools | No
TEL_L2300_A01_GM-1681 | [Application]"One More Brick"Game_Sound and Performance Problem-[User:Hilal] | Bug | 2018-03-07 16:51 | NotBug | A-Critical | 3rd app | No
TEL_L2300_A01_GM-1685 | GM8-Audio: Fail to Resume audio playing after whats-app/Skype call or video recording | Bug | 2018-03-05 17:33 | NotBug | B-Major | Call, Video | No
TEL_L2300_A01_GM-1686 | Unable to display the UI option on split screen during VT CALL. | Bug | 2018-02-26 11:11 | Unsured | B-Major | Call, Video |  | Not Tested need more info
TEL_L2300_A01_GM-1688 | Image preview is not clear in camera panorama mode | Bug | 2018-03-05 15:47 | Unsured | B-Major | Camera | Yes | GAO-191
TEL_L2300_A01_GM-1689 | Blur image is captured in panorama mode | Bug | 2018-03-05 15:43 | Unsured | B-Major | Camera | Yes | GAO-189
TEL_L2300_A01_GM-1692 | Panaroma_Screen flickering with pop up is observed for a second | Bug | 2018-03-27 19:01 | NotBug | C-Minor | Camera | Yes | GAO-185
TEL_L2300_A01_GM-1696 | DUT displayed Video call option on UI even though TTY enabled | Bug | 2018-03-07 22:38 | NotBug | B-Major | Call, Network | Yes | GAO-128
TEL_L2300_A01_GM-1697 | Phone app crashed while receiving missed call notifications after switching on mobile | Bug | 2018-03-06 11:47 | Suspended | B-Major | Call, Call History | No
TEL_L2300_A01_GM-1699 | Lux values are not displayed correctly from GM mobiles using sensor test app | Bug | 2018-03-26 23:39 | NotBug | B-Major | Sensor | No
TEL_L2300_A01_GM-1702 | The call disconnect during Handover[Turk_Telekom]-[User:Zeynep/Hilal] | Bug | 2018-03-27 18:06 | Suspended | A-Critical | Call |  | Not Tested -Turk_telecom
TEL_L2300_A01_GM-1703 | [General] Black Line Appear on top of the Screen | Bug | 2018-03-27 15:56 | NotBug | A-Critical | Lock screen, Main Screen | No
TEL_L2300_A01_GM-1705 | [Performance] PDF Download is very slow to view. Downloaded from Outlook app and used WPS office | Bug | 2018-03-12 19:45 | Unsured | B-Major | File Manager, System Tools | No
TEL_L2300_A01_GM-1706 | [Application] AnTuTu Bechmark [User:Zeynep] | Bug | 2018-03-08 16:14 | Unsured | B-Major | 3rd app | Yes | GAO-332
TEL_L2300_A01_GM-1707 | [*Y] Google Sharing Location İssue without account | Bug | 2018-04-04 23:09 | NotBug | C-Minor | GPS | Yes | GAO-331
TEL_L2300_A01_GM-1708 | [*Y] System UI freeze while GPS drive test | Bug | 2018-03-06 15:28 | NotBug | B-Major | GPS |  | Not Tested -Field Test
TEL_L2300_A01_GM-1712 | [Netherland] IMS Configuration | Bug | 2018-02-27 16:22 | NotBug | S-Blocking | Network |  | Not Tested-Netherland IMS setting Configuration
TEL_L2300_A01_GM-1713 | [Turkey FT/Istanbul]Conference call drop while trying to add a call in ongoing conference call after SRVCC for Turkcell Operator. | Bug | 2018-03-09 08:55 | Unsured | B-Major | Network |  | Not Tested- Turkcell and SRVCC
TEL_L2300_A01_GM-1717 | [Turkey FT/Istanbul Field Test][GM08]Device fails to make Vowifi call over secured WiFi for Turk Cell operator. | Bug | 2018-03-19 16:40 | Suspended | B-Major | Network, WiFi |  | Not Tested-Turkcell
TEL_L2300_A01_GM-1721 | [Field Test]Device fails to send IMS PDN connectivity request for SUB 2: Vodafone when inserted with international roaming in SUB 1 | Bug | 2018-03-19 10:11 | Suspended | A-Critical | Network |  | Not Tested- Field Test
TEL_L2300_A01_GM-1722 | [Field_Test]Device fails to merge ongoing VoWifi calls and gives error pop up “unable to conference” for Vodafone operator. | Bug | 2018-03-19 16:40 | Suspended | A-Critical | Network |  | Not Tested- Field Test
TEL_L2300_A01_GM-1723 | GMOffice_Thermal GPS Drive test with Video call is heating device till 55C | Bug | 2018-03-26 16:16 | Unsured | A-Critical | GPS |  | Not Tested-Thermal Test(raised in JIRA GAO-237)
TEL_L2300_A01_GM-1724 | Device took more than 8 minutes to send IMS PDN connectivity request and latch on IMS for Vodafone Operator | Bug | 2018-03-05 10:40 | Suspended | A-Critical | Network |  | Not Tested- Vodafone
TEL_L2300_A01_GM-1725 | GMOffice_System UI freeze while GPS drive test | Bug | 2018-02-28 17:27 | Unsured | A-Critical | GPS |  | Not Tested-Field Test
TEL_L2300_A01_GM-1726 | Error message popup is displaying message in other language when user select lyric without internet | Bug | 2018-03-06 20:55 | NotBug | B-Major | 3rd app | Yes | GAO-234
TEL_L2300_A01_GM-1728 | [Field Test]Device mobile originated long call drop observed on Vodafone Operator | Bug | 2018-03-05 09:49 | Unsured | A-Critical | Call, Network |  | Not Tested-Field Test
TEL_L2300_A01_GM-1737 | [Field Test] [Vodafone]Device near cell DL throughput performance is low as compare to reference. | Bug | 2018-03-14 11:44 | Suspended | A-Critical | Network |  | Not Tested-Field Test
TEL_L2300_A01_GM-1738 | Device near cell with CA active DL throughput performance is low as compare to reference. | Bug | 2018-03-14 11:44 | Suspended | A-Critical | Network |  | Not Tested-Turkcell
TEL_L2300_A01_GM-1739 | Language_Confusion [User: Zeynep] | Bug | 2018-05-16 20:32 | Suspended | B-Major | String | No
TEL_L2300_A01_GM-1747 | Connecting to bluetooth during a call | Bug | 2018-05-16 20:38 | Unsured | A-Critical | Bluetooth |  | Not Tested due to lack of Carkit
TEL_L2300_A01_GM-1755 | [UI] Headset Icon Stucked on UI | Bug | 2018-05-16 20:46 | NotBug | A-Critical | Main Screen, Settings | No
TEL_L2300_A01_GM-1756 | [App] Snapchat Issue [FC*] | Bug | 2018-04-27 17:06 | Unsured | A-Critical | 3rd app(operator) | Yes | GAO-333
TEL_L2300_A01_GM-1757 | [Vodafone] Conference Call - Initiation Type | Bug | 2018-03-19 16:42 | Suspended | C-Minor | Network |  | Not Tested-Vodafone
TEL_L2300_A01_GM-1764 | 【系统测试】重置WLAN、移动数据、蓝牙设置，点击“重置设置 ”按钮无反应，多次点击报错 | Bug | 2018-03-12 17:48 | NotBug | B-Major | Settings |  | Not Tested- not understood
TEL_L2300_A01_GM-1765 | [Vodafone] Volte Registration after Vowifi | Bug | 2018-03-23 10:09 | Suspended | A-Critical | Call, Network |  | Not Tested-Vodafone
TEL_L2300_A01_GM-1773 | [Network] [Vodafone] Can't attach to Network | Bug | 2018-03-21 16:43 | NotBug | S-Blocking | Network, Settings |  | Not Tested-Vodafone
TEL_L2300_A01_GM-1774 | There is no "OK Google" in the setup wizard flow | Bug | 2018-05-17 12:39 | NotBug | A-Critical | Lock screen, Main Screen, Settings | No
TEL_L2300_A01_GM-1776 | Voicemail Not Working (except Turkcell-Turkcell) | Bug | 2018-04-04 10:46 | Suspended | B-Major | 3rd app(operator) |  | Not Tested-TurkCell
TEL_L2300_A01_GM-1780 | [General] Blank White Screen after Lockscreen | Bug | 2018-05-17 13:10 | NotBug | B-Major | Lock screen, Main Screen |  | Not a Bug as per the GM comments
TEL_L2300_A01_GM-1784 | [Function] Bluetooth - Default Configuration | Bug | 2018-03-29 19:18 | NotBug | C-Minor | Bluetooth, Main Screen, Settings | No
TEL_L2300_A01_GM-1785 | <GM8-Issue>Getting call drops and IMS de-registration continuously on latest build OGM18F. | Bug | 2018-03-29 21:15 | NotBug | A-Critical | Network, Radio, Settings |  | Not Tested-TurkCell
TEL_L2300_A01_GM-1787 | Remove "Mobile plan" | Bug | 2018-05-17 13:40 | NotBug | C-Minor | Settings |  | NOT A BUG(Feature in mobile)
TEL_L2300_A01_GM-1788 | [General] Network Crash | Bug | 2018-05-17 13:44 | NotBug | A-Critical | Call, Network |  | Not an issue as per GM comments
TEL_L2300_A01_GM-1789 | Wifi and Mobil Data icons at Home Screen | Bug | 2018-05-17 13:52 | NotBug | C-Minor | Main Screen, WiFi |  | NOT A BUG(Feature in mobile)
TEL_L2300_A01_GM-1793 | [Network] MBN Configuration for IRAQ Operator | 需求 | 2018-05-08 16:05 | Unsured | A-Critical | Network |  | Not Tested-IRAQ Operator
TEL_L2300_A01_GM-1795 | [ Network ] Network Attach Fail | Bug | 2018-05-17 13:57 | NotBug | S-Blocking | Network | No
TEL_L2300_A01_GM-1796 | [Network ] Gm8 Plus can't attach Network again after no signal area | Bug | 2018-05-17 13:58 | NotBug | S-Blocking | Network | No
TEL_L2300_A01_GM-1797 | [General] Bugreport feature doesn't work on GM8 | Bug | 2018-04-27 16:17 | NotBug | B-Major | Settings, System Tools | No
TEL_L2300_A01_GM-1808 | [ Settings ] Default Notification Sound | 需求 | 2018-04-05 21:29 | NotBug | B-Major | Settings |  | NOT A BUG(Feature in mobile)
TEL_L2300_A01_GM-1809 | [Vodafone] Conferans Call Issue | Bug | 2018-04-06 16:48 | NotBug | B-Major | Call |  | Not Tested-Vodafone
TEL_L2300_A01_GM-1813 | [ Tele2- Operator Requirement ] Make IMS APN invisible | 需求 | 2018-05-01 08:59 | Unsured | A-Critical | Network, Settings |  | NOT A BUG(Feature in mobile)
TEL_L2300_A01_GM-1814 | [ Tele2- Operator Requirement ] USSD Codes not trigger CSFB, | 需求 | 2018-05-02 11:44 | Suspended | A-Critical | Network |  | Not Tested-Netherland setting Configuration
TEL_L2300_A01_GM-1815 | [ Tele2- Operator Requirement ] TCP / UDP Support Query | 需求 | 2018-05-01 09:02 | Unsured | B-Major | Network |  | Not Tested-Netherland setting Configuration
TEL_L2300_A01_GM-1816 | [General] Inter-Duplex-Mode Measurement Feature | Bug | 2018-04-27 16:16 | NotBug | B-Major | Antenna |  | Not Tested-Need more info
TEL_L2300_A01_GM-1817 | [ Update Request ] Android 8.1 Update | 需求 | 2018-04-26 20:37 | Suspended | S-Blocking | System Tools |  | NOT A BUG - generic question
TEL_L2300_A01_GM-1818 | [ Update Request ] Android P Release Beta Program | 需求 | 2018-04-23 11:06 | Suspended | A-Critical | System Tools |  | NOT A BUG - generic question
TEL_L2300_A01_GM-1826 | [Connectivity]5GHZ band is missing in Wi-Fi hotspot | Bug | 2018-04-16 15:13 | NotBug | A-Critical | WiFi | No
TEL_L2300_A01_GM-1829 | [Vodafone] Vilte Does Not Work | Bug | 2018-04-27 16:17 | NotBug | A-Critical | Network |  | Not Tested-TurkCell
TEL_L2300_A01_GM-1831 | [Main Screen] Icon placement | 需求 | 2018-04-17 16:05 | NotBug | S-Blocking | Lock screen, Main Screen |  | NOT A BUG -feature in mobile
TEL_L2300_A01_GM-1833 | [SRVCC] [Turkcell] During Video Call (MO to MT) gave "phone has stopped" pops up | Bug | 2018-05-04 19:13 | Suspended | B-Major | Call, Video |  | Not Tested-TurkCell
TEL_L2300_A01_GM-1845 | Camera doesn't open | Bug | 2018-04-26 21:50 | NotBug | A-Critical | Camera | No
TEL_L2300_A01_GM-1846 | Upgrade SW version | 研发自提单 | 2018-04-27 10:35 | Unsured | B-Major | Dailybuild |  | NOT A BUG - generic question
TEL_L2300_A01_GM-1848 | [GM8ONE]: Camera consuming more current:549mA than the reference value:284.5 | Bug | 2018-05-17 18:11 | Suspended | S-Blocking | Power Management |  | Not Tested- Lack of tool to measure the Current
TEL_L2300_A01_GM-1849 | [GM8ONE]: All the RF components consuming more current | Bug | 2018-05-03 09:59 | Unsured | S-Blocking | Power Management |  | Not Tested-Lack of tool to measure the power
TEL_L2300_A01_GM-1851 | [GM8ONE]: DUT unable to display GPS icon in the notification bar. | Bug | 2018-05-10 19:33 | NotBug | A-Critical | GPS |  | NOT A BUG as per the GM comments
TEL_L2300_A01_GM-1858 | [GM8 Android one]: Device neverg oing to deep sleep mode in DSDS W+G mode | Bug | 2018-05-14 22:50 | Unsured | S-Blocking | Power Management |  | Not Tested-Need more info
TEL_L2300_A01_GM-1870 | Change Writing in Settings | Bug | 2018-05-10 21:52 | NotBug | C-Minor | Settings | No
TEL_L2300_A01_GM-1905 | [GM 8]:<Third-party app >whatsapp crash occurs while sending screenshot (or)updating it as whatsapp status | Bug | 2018-05-17 19:27 | NotBug | S-Blocking | 3rd app | Yes | GAO-318